Sample Fundraiser Planning Timetable

Allow at least 7 weeks to plan the fundraiser (including follow-up).

# Week 1

- Notify your national and state society that you are planning the event.

- Invite several people to form an event committee.

- Facilitate a conference call with your committee to initiate the planning.

- Establish a list of prospective donors.

# Week 2

- Finalize the donor prospect list.

- Meet with the printer to review the invitation/fundraising letter.

# Week 3

- Facilitate a conference call with your event committee to finalize all planning and logistical issues for the fundraiser.

- Fax a draft of the event plans to your committee.

- Mail the invitation letter to prospective donors.

Week 4

1. Place follow-up calls to prospective donors.

Week 5

1. Complete follow-up calls to prospective donors.

# Week 6 (Week of Event)

- Give a final count of attendees to the caterer.

- Prepare name tags in advance of the event.

- Review your event flow and create a checklist of things to do.

- Enjoy the fundraiser.

# Week 7

- Send thank-you letters to donors and the candidate.

- Review donations and ensure that they correspond with commitments.

- Make follow-up calls for outstanding commitments.

- Review your budget and prepare accounting for the event committee.

- Deliver outstanding commitments to the candidate's campaign office.